## Sheet1
| Project Name: | AMI (Artifical Medical Intelligence) | [5 empty] | Weeks
| Team Members: | Stefano Buglione, Lauryn Brown, Marie Schwarz, Nicolas Fernandez | [5 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15
| Start Date: | 2026-01-05 | [5 empty] | 2026-01-12 | [27 empty] | 2026-02-09 | [27 empty] | Mar | [34 empty] | Apr
[8 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13
Task # | Activity Title | Tasks | Assigned To | Start Date | Due Date | Status | Completion % | time axis 2026-01-05 to 2026-04-19
1 | Team & Project Creation | Team Recruitment |  | 2026-01-05 | 2026-01-07 | Complete | 100%
|  | Project Idea |  | 2026-01-05 | 2026-01-12 | Complete | 100%
|  | Project Prospectus |  | 2026-01-12 | 2026-01-23 | Complete | 100%
|  | Group Meetings |  | Saturday | 8PM EST | In Progress | 25%
2 | Requirements Phase | Define system scope and contraints |  | 2026-01-12 | 2026-01-30 | Complete | 100%
|  | identify user roles and use cases |  | 2026-02-01 | 2026-02-08 | In Progress | 0%
|  | Formalize functional requirements |  | 2026-01-30 | 2026-02-05 | In Progress | 0%
|  | Formalize non-functional requirements(LLM, ethics, and privacy laws) |  | 2026-02-04 | 2026-02-09 | In Progress | 95%
|  | Draft initial SRS (Software Requirements Specification) |  | 2026-02-06 | 2026-02-14 | In Progress | 0%
|  | Define AI avatar requirements |  | 2026-02-06 | 2026-02-14 | In Progress | 0%
3 | Analysis Phase | Analyze existing AI medical systems |  | 2026-02-15 | 2026-02-20 | Not Started | 0%
|  | Dataset and source evaluation |  | 2026-02-15 | 2026-02-25 | Not Started | 0%
|  | Analyze bias and hallucination risks |  | 2026-02-18 | 2026-02-28 | Not Started | 0%
|  | Feasability for avatar tools analysis |  | 2026-02-20 | 2026-03-01 | Not Started | 0%
|  | Finalize system requirements |  | 2026-02-20 | 2026-03-05 | Not Started | 0%
4 | Design Phase | System architecture design |  | 2026-03-06 | 2026-03-12 | Not Started | 0%
|  | LLM training pipeline and deployment design |  | 2026-03-06 | 2026-03-18 | Not Started | 0%
|  | UI/UX wireframes |  | 2026-03-10 | 2026-03-20 | Not Started | 0%
|  | Design AMI avatar appearance and behavior |  | 2026-03-06 | 2026-03-22 | Not Started | 0%
|  | Design source transparency and citation system |  | 2026-03-15 | 2026-03-25 | Not Started | 0%
5 | Implementation Phase | Set up chatbot framework |  | 2026-03-21 | 2026-03-28 | Not Started | 0%
|  | Implement response generation |  | 2026-03-25 | 2026-04-02 | Not Started | 0%
|  | Integrate APIs |  | 2026-03-28 | 2026-04-05 | Not Started | 0%
|  | Implement text-to-speech |  | 2026-03-30 | 2026-04-03 | Not Started | 0%
|  | Frontend implementation |  | 2026-04-01 | 2026-04-05 | Not Started | 0%
6 | Test Phase | Acquiring additional test data (using PRISMA) |  | 2026-03-27 | 2026-04-03 | Not Started | 0%
|  | Drafting test cases |  | 2026-03-27 | 2026-04-02 | Not Started | 0%
|  | Running test cases |  | 2026-04-01 | 2026-04-07 | Not Started | 0%
|  | Evaluate chatbot performance (accuracy, latency) |  | 2026-04-03 | 2026-04-09 | Not Started | 0%
|  | Conduct internal usability testing and team review |  | 2026-04-05 | 2026-04-10 | Not Started | 0%
7 | Delivery | Due Date |  | 2026-04-17 | 2026-04-17 | Not Started | 0%
|  | Project Demonstration |  | 2026-04-10 | 2026-04-17 | Not Started | 0%
|  | Final SRS |  | 2026-04-03 | 2026-04-10 | Not Started | 0%
|  | Peer Review |  | 2026-04-10 | 2026-04-17 | Not Started | 0%
Statuses
Not Started
In Progress
Running Issues
Complete
Formulas:
Weeks = IF(MONTH([AMI (Artifical Medical Intelligence), row above]-WEEKDAY(([AMI (Artifical Medical Intelligence), row above]),2)+1)<MONTH([AMI (Artifical Medical Intelligence), row above]),([AMI (Artifical Medical Intelligence), row above]-28-DAY([AMI (Artifical Medical Intelligence), row above])+7)-WEEKDAY(([AMI (Artifical Medical Intelligence), row above]-DAY([AMI (Artifical Medical Intelligence), row above])+7),2)+1,([AMI (Artifical Medical Intelligence), row above]-DAY([AMI (Artifical Medical Intelligence), row above])+7)-WEEKDAY(([AMI (Artifical Medical Intelligence), row above]-DAY([AMI (Artifical Medical Intelligence), row above])+7),2)+1)